## SUMMARY
| 2020-09-20 | 2020-10-20 | 2020-11-20 | 2020-12-20 | 2020-01-21 | 2020-02-21 | 2020-03-21 | 2020-04-21 | 2020-05-21 | 2020-06-21
OECCUL
Executing Loan guarantee scheme |  | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE
CTI
Execute Partnership /fiscal sponsorship/ tech assistance agreement |  | TRUE | TRUE | TRUE
Board development (review of Mem&Arts, matrix, recruitment, AGM) |  | TRUE | TRUE | TRUE
Review and Improve Governance |  | TRUE | TRUE | TRUE
SEEP
Concept paper | TRUE
Execute Partnership /fiscal sponsorship/ tech assistance agreement |  | TRUE | TRUE | TRUE
Create business plan and budgets |  | TRUE
Create strategic plan and budgets |  | TRUE
Create 30 60 90 day plan |  | TRUE
Executing 30 60 90 day plan pre MD appointment |  | TRUE | TRUE | TRUE
Drafting policies and procedures pre MD appointment |  | TRUE | TRUE | TRUE
Recruitment process for ED/staff (JD & recruitment) |  | TRUE | TRUE | TRUE
Board development (review of Mem&Arts, matrix, recruitment, AGM) |  | TRUE | TRUE | TRUE | TRUE
Review and Improve Governance |  |  |  | TRUE | TRUE | TRUE
EACC
Concept paper |  |  | TRUE
Execute Partnership /fiscal sponsorship/ tech assistance agreement |  |  | TRUE | TRUE
Create business plan and budgets |  |  |  | TRUE
Create strategic plan and budgets |  |  |  | TRUE
Create 30 60 90 day plan |  |  |  | TRUE
Executing 30 60 90 day plan pre MD appointment |  |  |  | TRUE | TRUE | TRUE
Drafting policies and procedures pre MD appointment |  |  |  | TRUE | TRUE | TRUE
Recruitment process for ED/staff (JD & recruitment) |  |  |  | TRUE | TRUE | TRUE
Board development (review of Mem&Arts, matrix, recruitment, AGM) |  |  |  | TRUE | TRUE | TRUE | TRUE
Review and Improve Governance | [5 empty] | TRUE | TRUE | TRUE
BCOP/Cancer Society Eleuthera |  |  |  |  | TRUE
Concept paper |  |  |  |  | TRUE | TRUE
Execute Partnership /fiscal sponsorship/ tech assistance agreement | [5 empty] | TRUE
Create business plan and budgets | [5 empty] | TRUE
Create strategic plan and budgets | [5 empty] | TRUE
Create 30 60 90 day plan | [5 empty] | TRUE | TRUE | TRUE
Executing 30 60 90 day plan pre MD appointment | [5 empty] | TRUE | TRUE | TRUE
Drafting policies and procedures pre MD appointment | [5 empty] | TRUE | TRUE | TRUE
Recruitment process for ED/staff (JD & recruitment) | [5 empty] | TRUE | TRUE | TRUE | TRUE
Board development (review of Mem&Arts, matrix, recruitment, AGM) | [7 empty] | TRUE | TRUE | TRUE
Review and Improve Governance
ISLAND JOURNEYS
Concept paper | [5 empty] | TRUE
Execute Partnership /fiscal sponsorship/ tech assistance agreement | [5 empty] | TRUE | TRUE
Create business plan and budgets | [6 empty] | TRUE
Create strategic plan and budgets | [6 empty] | TRUE
Create 30 60 90 day plan | [6 empty] | TRUE
Executing 30 60 90 day plan pre MD appointment | [6 empty] | TRUE | TRUE | TRUE
Drafting policies and procedures pre MD appointment | [6 empty] | TRUE | TRUE | TRUE
Recruitment process for ED/staff (JD & recruitment) | [6 empty] | TRUE | TRUE | TRUE
Board development (review of Mem&Arts, matrix, recruitment, AGM) | [6 empty] | TRUE | TRUE | TRUE | TRUE
Review and Improve Governance | [8 empty] | TRUE | TRUE
SOUTH ELEUTHERA MISSION
Execute Partnership /fiscal sponsorship/ tech assistance agreement
Review business plan and budgets | [6 empty] | TRUE
Review strategic plan and budgets | [6 empty] | TRUE
Drafting policies and procedures | [7 empty] | TRUE | TRUE | TRUE
Board development (review of Mem&Arts, matrix, recruitment, AGM) | [7 empty] | TRUE | TRUE | TRUE
Review and Improve Governance | [9 empty] | TRUE

## SEEP
SEEP | 2020-09-20 | 2020-10-20 | 2020-11-20 | 2020-12-20 | 2021-01-20 | 2021-02-20 | 2021-03-20 | 2021-04-20 | 2021-05-20 | 2021-06-20
Stakeholder meeting #1 to determine needs | 2020-09-20: TRUE
Carry Out Assessment to ascertain baseline | 2020-09-20: TRUE
Review existing Partnership Agreement (if available) | 2020-09-20: TRUE
Review governance structure | 2020-09-20: TRUE
Review strategic plan if any | 2020-09-20: TRUE
Review business plan if any | 2020-09-20: TRUE
Review financial information/budgets if any | 2020-09-20: TRUE
Prepare concept note (if required) | 2020-09-20: TRUE
Review board governance | 2020-09-20: TRUE
Stakeholder meeting #2 to determine way forward priorities timelines | 2020-10-20: TRUE
Draft website brief (if required) | 2020-10-20: TRUE
Draft MOU / Partnership / Fiscal sponsorship / Technical assistance agreement | 2020-10-20: TRUE; 2020-11-20: TRUE
Draft 30 60 90 Day Plan (if required) | 2020-10-20: TRUE
Start executing 30 60 90 Day plan until ED appointed (if required) | 2020-10-20: TRUE
Continue executing 30 60 90 Day plan until ED appointed (if required) | 2020-11-20: TRUE
Continue executing 30 60 90 Day plan until ED appointed (if required) | 2020-12-20: TRUE
Create strategic plan if missing | 2020-10-20: TRUE
Create business plan is missing | 2020-10-20: TRUE
Create budget for business plan | 2020-10-20: TRUE
Create budget for strategic plan | 2020-10-20: TRUE
StART Funding for organisation | 2020-10-20: TRUE
Continue Funding for organisation | 2020-11-20: TRUE
Continue Funding for organisation | 2020-12-20: TRUE
Create Theory of Change | 2020-10-20: TRUE
Create organisational chart | 2020-10-20: TRUE
Set monitoring and evaluation indicators for success | 2020-10-20: TRUE
Board to approve business plan | 2020-10-20: TRUE
Board to approve strategic plan | 2020-10-20: TRUE
Board to approve budgets | 2020-10-20: TRUE
Sign MOU / Partnership / Fiscal sponsorship / Technical assistance agreement | 2020-12-20: TRUE
create website (if required) | 2020-10-20: TRUE
Determine policies and procedures that require drafting | 2020-10-20: TRUE
Review Board structure | 2020-10-20: TRUE
Review Mem & Arts | 2020-10-20: TRUE
Create board matrix | 2020-10-20: TRUE
Identify possible board members | 2020-10-20: TRUE
draft JD for ED / staff | 2020-10-20: TRUE
Create board welcome pack based on Mem & Arts | 2020-10-20: TRUE
Board to approve JD | 2020-10-20: TRUE
Advertise ED/ staff position | 2020-10-20: TRUE
Short list ED/ staff position | 2020-10-20: TRUE
Interview ED/ staff position | 2020-11-20: TRUE
Start drafting policies and procedures | 2020-11-20: TRUE
Continue drafting policies and procedures | 2020-12-20: TRUE
Continue drafting policies and procedures | 2021-01-20: TRUE
Start recruiting board members | 2020-11-20: TRUE
Continue recruiting board members | 2020-12-20: TRUE
Reviewing Mem & Arts | 2020-12-20: TRUE
Appoint ED/ staff position | 2020-12-20: TRUE
Board approve ED | 2021-01-20: TRUE
Draft resolutions appointing board members | 2021-01-20: TRUE
AGM to appoint board members | 2021-01-20: TRUE
Draft paper on recommendations for chage to Mem & Arts | 2021-01-20: TRUE
Board orientation | 2021-02-20: TRUE
Special meeting to amend Mem & Arts | 2021-02-20: TRUE

## EACC
EACC | 2020-09-20 | 2020-10-20 | 2020-11-20 | 2020-12-20 | 2021-01-21 | 2021-02-21 | 2021-03-21 | 2021-04-21 | 2021-05-21 | 2021-06-21
Stakeholder meeting #1 to determine needs | 2020-11-20: TRUE
Carry Out Assessment to ascertain baseline | 2020-11-20: TRUE
Review existing Partnership Agreement (if available) | 2020-11-20: TRUE
Review governance structure | 2020-11-20: TRUE
Review strategic plan if any | 2020-11-20: TRUE
Review business plan if any | 2020-11-20: TRUE
Review financial information/budgets if any | 2020-11-20: TRUE
Prepare concept note (if required) | 2020-11-20: TRUE
Review board governance | 2020-11-20: TRUE
Stakeholder meeting #2 to determine way forward priorities timelines | 2020-12-20: TRUE
Draft website brief (if required) | 2020-12-20: TRUE
Draft MOU / Partnership / Fiscal sponsorship / Technical assistance agreement | 2020-12-20: TRUE
Draft 30 60 90 Day Plan (if required) | 2020-12-20: TRUE
Start executing 30 60 90 Day plan until ED appointed (if required) | 2020-12-20: TRUE
Continue executing 30 60 90 Day plan until ED appointed (if required) | 2021-01-21: TRUE
Continue executing 30 60 90 Day plan until ED appointed (if required) | 2021-02-21: TRUE
Create strategic plan if missing | 2020-12-20: TRUE
Create business plan is missing | 2020-12-20: TRUE
Create budget for business plan | 2020-12-20: TRUE
Create budget for strategic plan | 2020-12-20: TRUE
StART Funding for organisation | 2020-12-20: TRUE
Continue Funding for organisation | 2021-01-21: TRUE
Continue Funding for organisation | 2021-02-21: TRUE
Create Theory of Change | 2020-12-20: TRUE
Create organisational chart | 2020-12-20: TRUE
Set monitoring and evaluation indicators for success | 2020-12-20: TRUE
Board to approve business plan | 2020-12-20: TRUE
Board to approve strategic plan | 2020-12-20: TRUE
Board to approve budgets | 2020-12-20: TRUE
Sign MOU / Partnership / Fiscal sponsorship / Technical assistance agreement | 2020-12-20: TRUE
create website (if required) | 2020-12-20: TRUE
Determine policies and procedures that require drafting | 2020-12-20: TRUE
Review Board structure | 2020-12-20: TRUE
Review Mem & Arts | 2020-12-20: TRUE
Create board matrix | 2020-12-20: TRUE
Identify possible board members | 2020-12-20: TRUE
draft JD for ED / staff | 2020-12-20: TRUE
Create board welcome pack based on Mem & Arts | 2020-12-20: TRUE
Board to approve JD | 2020-12-20: TRUE
Advertise ED/ staff position | 2020-12-20: TRUE
Short list ED/ staff position | 2020-12-20: TRUE
Interview ED/ staff position | 2021-01-21: TRUE
Start drafting policies and procedures | 2021-01-21: TRUE
Continue drafting policies and procedures | 2021-02-21: TRUE
Continue drafting policies and procedures | 2021-03-21: TRUE
Start recruiting board members | 2021-01-21: TRUE
Continue recruiting board members | 2021-02-21: TRUE
Reviewing Mem & Arts | 2021-02-21: TRUE
Appoint ED/ staff position | 2021-03-21: TRUE
Board approve ED | 2021-03-21: TRUE
Draft resolutions appointing board members | 2021-03-21: TRUE
AGM to appoint board members | 2021-04-21: TRUE
Draft paper on recommendations for chage to Mem & Arts | 2021-04-21: TRUE
Board orientation | 2021-04-21: TRUE
Special meeting to amend Mem & Arts | 2021-04-21: TRUE

## IJ
ISLAND JOURNEYS (IJ) | 2020-09-20 | 2020-10-20 | 2020-11-20 | 2020-12-20 | 2021-01-21 | 2021-02-21 | 2021-03-21 | 2021-04-21 | 2021-05-21 | 2021-06-21
Stakeholder meeting #1 to determine needs | 2020-12-20: TRUE
Carry Out Assessment to ascertain baseline | 2020-12-20: TRUE
Review existing Partnership Agreement (if available) | 2020-12-20: TRUE
Review governance structure | 2021-01-21: TRUE
Review strategic plan if any | 2021-01-21: TRUE
Review business plan if any | 2021-01-21: TRUE
Review financial information/budgets if any | 2021-01-21: TRUE
Prepare concept note (if required) | 2021-01-21: TRUE
Review board governance | 2021-01-21: TRUE
Stakeholder meeting #2 to determine way forward priorities timelines | 2021-02-21: TRUE
Draft website brief (if required) | 2021-02-21: TRUE
Draft MOU / Partnership / Fiscal sponsorship / Technical assistance agreement | 2020-12-20: TRUE
Draft 30 60 90 Day Plan (if required) | 2021-02-21: TRUE
Start executing 30 60 90 Day plan until ED appointed (if required) | 2021-02-21: TRUE
Continue executing 30 60 90 Day plan until ED appointed (if required) | 2021-03-21: TRUE
Continue executing 30 60 90 Day plan until ED appointed (if required) | 2021-04-21: TRUE
Create strategic plan if missing | 2021-02-21: TRUE
Create business plan is missing | 2021-02-21: TRUE
Create budget for business plan | 2021-02-21: TRUE
Create budget for strategic plan | 2021-02-21: TRUE
StART Funding for organisation | 2021-02-21: TRUE
Continue Funding for organisation | 2021-03-21: TRUE
Continue Funding for organisation | 2021-04-21: TRUE
Create Theory of Change | 2021-02-21: TRUE
Create organisational chart | 2021-02-21: TRUE
Set monitoring and evaluation indicators for success | 2021-02-21: TRUE
Board to approve business plan | 2021-02-21: TRUE
Board to approve strategic plan | 2021-02-21: TRUE
Board to approve budgets | 2021-02-21: TRUE
Sign MOU / Partnership / Fiscal sponsorship / Technical assistance agreement | 2020-12-20: TRUE
create website (if required) | 2021-02-21: TRUE
Determine policies and procedures that require drafting | 2021-02-21: TRUE
Review Board structure | 2021-02-21: TRUE
Review Mem & Arts | 2021-02-21: TRUE
Create board matrix | 2021-02-21: TRUE
Identify possible board members | 2021-02-21: TRUE
draft JD for ED / staff | 2021-02-21: TRUE
Create board welcome pack based on Mem & Arts | 2021-02-21: TRUE
Board to approve JD | 2021-02-21: TRUE
Advertise ED/ staff position | 2021-02-21: TRUE
Short list ED/ staff position | 2021-02-21: TRUE
Interview ED/ staff position | 2021-03-21: TRUE
Start drafting policies and procedures | 2021-03-21: TRUE
Continue drafting policies and procedures | 2021-04-21: TRUE
Continue drafting policies and procedures | 2021-05-21: TRUE
Start recruiting board members | 2021-03-21: TRUE
Continue recruiting board members | 2021-04-21: TRUE
Reviewing Mem & Arts | 2021-04-21: TRUE
Appoint ED/ staff position | 2021-05-21: TRUE
Board approve ED | 2021-05-21: TRUE
Draft resolutions appointing board members | 2021-05-21: TRUE
AGM to appoint board members | 2021-06-21: TRUE
Draft paper on recommendations for chage to Mem & Arts | 2021-06-21: TRUE
Board orientation | 2021-06-21: TRUE
Special meeting to amend Mem & Arts | 2021-06-21: TRUE

## SEM
SOUTH ELEUTHERA MISSION (SEM) | 2020-09-20 | 2020-10-20 | 2020-11-20 | 2020-12-20 | 2021-01-21 | 2021-02-21 | 2021-03-21 | 2021-04-21 | 2021-05-21 | 2021-06-21
Stakeholder meeting #1 to determine needs | 2021-03-21: TRUE
Carry Out Assessment to ascertain baseline | 2021-03-21: TRUE
Review existing Partnership Agreement (if available) | 2020-12-20: TRUE
Review governance structure | 2021-03-21: TRUE
Review strategic plan if any | 2021-03-21: TRUE
Review business plan if any | 2021-03-21: TRUE
Review financial information/budgets if any | 2021-03-21: TRUE
Prepare concept note (if required) | 2021-03-21: TRUE
Review board governance | 2021-03-21: TRUE
Stakeholder meeting #2 to determine way forward priorities timelines | 2021-04-21: TRUE
Draft website brief (if required) | 2021-04-21: TRUE
Draft MOU / Partnership / Fiscal sponsorship / Technical assistance agreement | 2020-12-20: TRUE
Draft 30 60 90 Day Plan (if required) | 2021-04-21: TRUE
Start executing 30 60 90 Day plan until ED appointed (if required) | 2021-04-21: TRUE
Continue executing 30 60 90 Day plan until ED appointed (if required) | 2021-05-21: TRUE
Continue executing 30 60 90 Day plan until ED appointed (if required) | 2021-06-21: TRUE
Create strategic plan if missing (if required) | 2021-04-21: TRUE
Create business plan is missing (if required) | 2021-04-21: TRUE
Create budget for business plan (if required) | 2021-04-21: TRUE
Create budget for strategic plan (if required) | 2021-04-21: TRUE
StART Funding for organisation | 2021-04-21: TRUE
Continue Funding for organisation | 2021-05-21: TRUE
Continue Funding for organisation | 2021-06-21: TRUE
Create Theory of Change (if required) | 2021-04-21: TRUE
Create organisational chart (if required) | 2021-04-21: TRUE
Set monitoring and evaluation indicators for success (if required) | 2021-04-21: TRUE
Board to approve business plan | 2021-04-21: TRUE
Board to approve strategic plan | 2021-04-21: TRUE
Board to approve budgets | 2021-04-21: TRUE
Sign MOU / Partnership / Fiscal sponsorship / Technical assistance agreement | 2020-12-20: TRUE
Determine policies and procedures that require drafting | 2021-04-21: TRUE
Review Board structure | 2021-04-21: TRUE
Review Mem & Arts | 2021-04-21: TRUE
Create board matrix | 2021-04-21: TRUE
Identify possible board members | 2021-04-21: TRUE
Create board welcome pack based on Mem & Arts | 2021-04-21: TRUE
Start drafting policies and procedures | 2021-05-21: TRUE
Continue drafting policies and procedures | 2021-06-21: TRUE
Continue drafting policies and procedures | [10 empty] | TRUE
Start recruiting board members | 2021-05-21: TRUE
Continue recruiting board members | 2021-06-21: TRUE
Reviewing Mem & Arts | 2021-06-21: TRUE
Draft resolutions appointing board members | 2021-06-21: TRUE
AGM to appoint board members | [10 empty] | TRUE
Draft paper on recommendations for chage to Mem & Arts | [10 empty] | TRUE
Board orientation | [11 empty] | TRUE
Special meeting to amend Mem & Arts | [11 empty] | TRUE